## excel(4)
Proyecto/Tarea | Fase | Tiempo Inicio | Delta | InterrupciÃ³n | Comentario
/Non Project/PSP Fundamentals & Advanced/Program 3 | Planning | mar 05, 2017 08:51:41 PM | 164 | 0 | Tomo mas tiempo del esperado por confucion en diligenciamiento de formatos
/Non Project/PSP Fundamentals & Advanced/Program 3 | Design | mar 05, 2017 11:35:40 PM | 45 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Design Review | mar 06, 2017 12:20:35 AM | 21 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Code | mar 06, 2017 12:42:05 AM | 127 | 0 | Se detuvo procesos para trabajar en tarea de anÃ¡lisis de sofware
/Non Project/PSP Fundamentals & Advanced/Program 3 | Code | mar 06, 2017 07:08:38 PM | 174 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Code | mar 07, 2017 12:20:58 AM | 66 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Code Review | mar 07, 2017 01:27:10 AM | 34 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Compile | mar 07, 2017 02:01:11 AM | 5 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Test | mar 07, 2017 02:06:23 AM | 14 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Postmortem | mar 07, 2017 11:19:10 PM | 77 | 0